## Risk Register
Risk ID | Asset | Threat | Vulnerability | Likelihood | Impact | Risk Score | Rating | Risk Owner | Existing Controls (simulated) | Treatment Option | Treatment Action | Control Reference (Annex A) | Target Date | Residual Likelihood | Residual Impact | Residual Score | Residual Rating | Status | Risk Acceptance
R-001 | Customer DB | Data breach | Excessive privileges | 4 | 5 | 20 | Critical | CTO | Role-based DB users; no periodic review | Mitigate | Conduct quarterly database access reviews; remove standing admin access | A.5.15, A.5.18, A.8.2 | 2026-11-07 | 2 | 4 | 8 | Medium | Open | Not accepted - treat
R-002 | AWS | Cloud compromise | Misconfigured IAM | 3 | 5 | 15 | High | DevOps Lead | IAM roles in use; no formal permission review | Mitigate | Review AWS IAM permissions; enable IAM Access Analyzer | A.5.23, A.8.2 | 2026-11-07 | 2 | 4 | 8 | Medium | Open | Not accepted - treat
R-003 | GitHub | Account takeover | MFA not enforced | 3 | 5 | 15 | High | Engineering Lead | MFA available, not enforced for all | Mitigate | Enforce MFA on GitHub org | A.5.17, A.8.5 | 2026-10-23 | 1 | 5 | 5 | Medium | In Progress | Not accepted - treat
R-004 | Laptops | Malware | Weak endpoint controls | 4 | 4 | 16 | High | IT Manager | Basic AV on some devices | Mitigate | Deploy endpoint protection (EDR) on all laptops | A.8.7, A.8.1 | 2026-11-22 | 2 | 3 | 6 | Medium | In Progress | Not accepted - treat
R-005 | M365 | Phishing | Limited awareness | 4 | 4 | 16 | High | HR / Security Lead | Spam filtering | Mitigate | Conduct phishing simulation and security awareness training | A.6.3, A.8.23 | 2026-11-07 | 3 | 3 | 9 | Medium | Open | Not accepted - treat
R-006 | VPN | Unauthorized access | Weak authentication | 3 | 5 | 15 | High | IT Manager | Password-only VPN login | Mitigate | Enforce MFA on VPN | A.5.15, A.8.5 | 2026-11-07 | 2 | 4 | 8 | Medium | Open | Not accepted - treat
R-007 | Backup | Data loss | Inadequate backup testing | 3 | 5 | 15 | High | DevOps Lead | Daily cloud backups; no restore tests | Mitigate | Perform quarterly backup restoration test | A.8.13 | 2026-11-07 | 2 | 4 | 8 | Medium | Open | Not accepted - treat
R-008 | API Keys | Credential exposure | Poor secret management | 3 | 5 | 15 | High | DevOps Lead | Some secrets in env files | Mitigate | Move secrets to AWS Secrets Manager; enable GitHub secret scanning | A.5.17, A.8.24 | 2026-11-22 | 2 | 4 | 8 | Medium | Open | Not accepted - treat
R-009 | HR System | Data disclosure | Excessive access | 3 | 4 | 12 | High | HR Manager | Admin role limited to HR team (not reviewed) | Mitigate | Review and restrict HRMS roles | A.5.18 | 2026-11-07 | 2 | 3 | 6 | Medium | Open | Not accepted - treat
R-010 | Customer Support | Data leakage | Improper data handling | 3 | 4 | 12 | High | Support Lead | Informal guidance to agents | Mitigate | Define data-handling procedure; mask customer data in tickets | A.5.34, A.8.11 | 2026-11-22 | 2 | 3 | 6 | Medium | Open | Not accepted - treat
R-011 | Source Code | Intellectual property theft | Excessive repository access | 3 | 4 | 12 | High | Engineering Lead | Team-level repo permissions | Mitigate | Repository access review; branch protection; least privilege | A.8.4, A.5.18 | 2026-11-07 | 2 | 3 | 6 | Medium | Open | Not accepted - treat
R-012 | AWS | Service outage | Single-region dependency | 3 | 5 | 15 | High | DevOps Lead | Multi-AZ for database (assumed) | Mitigate | Design and test multi-region / DR failover | A.8.14, A.5.30 | 2027-01-06 | 2 | 4 | 8 | Medium | Open | Not accepted - treat
R-013 | Security Logs | Evidence loss | Insufficient retention | 3 | 4 | 12 | High | Security Lead | Default log retention only | Mitigate | Define 12-month retention; centralise logs in protected storage | A.8.15, A.8.16 | 2026-11-22 | 2 | 3 | 6 | Medium | Open | Not accepted - treat
R-014 | Employee Laptop | Data theft | Disk encryption gap | 3 | 4 | 12 | High | IT Manager | Encryption on some devices | Mitigate | Enforce full-disk encryption through device management | A.8.1, A.8.24 | 2026-11-07 | 1 | 4 | 4 | Low | Open | Not accepted - treat
R-015 | Vendor | Supply-chain compromise | Weak vendor assessment | 3 | 5 | 15 | High | Procurement | Contracts reviewed ad hoc | Mitigate | Implement vendor security assessment process | A.5.19, A.5.20 | 2026-12-07 | 2 | 4 | 8 | Medium | Open | Not accepted - treat
R-016 | Website | Exploitation | Unpatched components | 3 | 4 | 12 | High | IT Manager | Manual updates | Mitigate | Monthly patching and vulnerability scanning for website | A.8.8 | 2026-11-07 | 2 | 3 | 6 | Medium | Open | Not accepted - treat
R-017 | Payroll Data | Unauthorized disclosure | Weak access segregation | 2 | 5 | 10 | High | Finance Manager | Payroll accessible to finance team | Mitigate | Restrict payroll access to named roles; log access | A.5.15, A.8.3, A.5.3 | 2026-11-07 | 1 | 5 | 5 | Medium | Open | Not accepted - treat
R-018 | Network | Lateral movement | Poor segmentation | 3 | 4 | 12 | High | DevOps Lead | Single flat corporate network (assumed) | Mitigate | Segment prod/corporate/dev; review security groups | A.8.22, A.8.20 | 2026-12-07 | 2 | 3 | 6 | Medium | Open | Not accepted - treat

## Summary
Risk summary (live formulas from Risk Register)
Rating | Inherent count | Residual count
Critical | 1 | 0
High | 17 | 0
Medium | 0 | 17
Low | 0 | 1
Total | 18 | 18
Assumptions: existing controls, owners, target dates and residual scores are simulated. Target dates = project start 08-Oct-2026 + treatment days. Residual risk is the expected score once treatment is complete.