## Risk Treatment Plan
Risk ID | Asset | Inherent Rating | Treatment | Action | Owner | Timeline | Target Date | Status | Score: Inherent -> Residual
R-001 | Customer DB | Critical | Mitigate | Conduct quarterly database access reviews; remove standing admin access | CTO | 30 days | 2026-11-07 | Open | 20 -> 8
R-002 | AWS | High | Mitigate | Review AWS IAM permissions; enable IAM Access Analyzer | DevOps Lead | 30 days | 2026-11-07 | Open | 15 -> 8
R-003 | GitHub | High | Mitigate | Enforce MFA on GitHub org | Engineering Lead | 15 days | 2026-10-23 | In Progress | 15 -> 5
R-004 | Laptops | High | Mitigate | Deploy endpoint protection (EDR) on all laptops | IT Manager | 45 days | 2026-11-22 | In Progress | 16 -> 6
R-005 | M365 | High | Mitigate | Conduct phishing simulation and security awareness training | HR/Security | 30 days | 2026-11-07 | Open | 16 -> 9
R-006 | VPN | High | Mitigate | Enforce MFA on VPN | IT Manager | 30 days | 2026-11-07 | Open | 15 -> 8
R-007 | Backup | High | Mitigate | Perform quarterly backup restoration test | DevOps Lead | 30 days | 2026-11-07 | Open | 15 -> 8
R-008 | API Keys | High | Mitigate | Move secrets to AWS Secrets Manager; enable GitHub secret scanning | DevOps Lead | 45 days | 2026-11-22 | Open | 15 -> 8
R-009 | HR System | High | Mitigate | Review and restrict HRMS roles | HR Manager | 30 days | 2026-11-07 | Open | 12 -> 6
R-010 | Customer Support | High | Mitigate | Define data-handling procedure; mask customer data in tickets | Support Lead | 45 days | 2026-11-22 | Open | 12 -> 6
R-011 | Source Code | High | Mitigate | Repository access review; branch protection; least privilege | Engineering Lead | 30 days | 2026-11-07 | Open | 12 -> 6
R-012 | AWS | High | Mitigate | Design and test multi-region / DR failover | DevOps Lead | 90 days | 2027-01-06 | Open | 15 -> 8
R-013 | Security Logs | High | Mitigate | Define 12-month retention; centralise logs in protected storage | Security Lead | 45 days | 2026-11-22 | Open | 12 -> 6
R-014 | Employee Laptop | High | Mitigate | Enforce full-disk encryption through device management | IT Manager | 30 days | 2026-11-07 | Open | 12 -> 4
R-015 | Vendor | High | Mitigate | Implement vendor security assessment process | Procurement | 60 days | 2026-12-07 | Open | 15 -> 8
R-016 | Website | High | Mitigate | Monthly patching and vulnerability scanning for website | IT Manager | 30 days | 2026-11-07 | Open | 12 -> 6
R-017 | Payroll Data | High | Mitigate | Restrict payroll access to named roles; log access | Finance Manager | 30 days | 2026-11-07 | Open | 10 -> 5
R-018 | Network | High | Mitigate | Segment prod/corporate/dev; review security groups | DevOps Lead | 60 days | 2026-12-07 | Open | 12 -> 6

## Notes
Note
R | a | t | i | n | g | s |  | a | n | d |  | s | c | o | r | e | s |  | m | i | r | r | o | r |  | R | i | s | k | - | R | e | g | i | s | t | e | r | . | x | l | s | x |  | ( | s | t | a | t | i | c |  | c | o | p | y |  | - |  | u | p | d | a | t | e |  | b | o | t | h |  | t | o | g | e | t | h | e | r | ) | .
R | - | 0 | 0 | 3 |  | s | h | o | w | n |  | a | s |  | I | n |  | P | r | o | g | r | e | s | s |  | r | a | t | h | e | r |  | t | h | a | n |  | C | o | m | p | l | e | t | e | : |  | o | r | g | - | w | i | d | e |  | M | F | A |  | c | o | v | e | r | a | g | e |  | i | s |  | 8 | 2 | % |  | i | n |  | t | h | e |  | m | a | n | a | g | e | m | e | n | t | - | r | e | v | i | e | w |  | K | P | I | s | , | s | o | c | l | o | s | i | n | g | t | h | e | r | i | s | k | w | o | u | l | d | b | e | i | n | c | o | n | s | i | s | t | e | n | t | w | i | t | h | a | u | d | i | t | e | v | i | d | e | n | c | e | .
T | r | e | a | t | m | e | n | t |  | o | p | t | i | o | n |  | f | o | r |  | a | l | l |  | 1 | 8 |  | r | i | s | k | s |  | i | s |  | M | i | t | i | g | a | t | e | ; |  | r | i | s | k |  | a | p | p | e | t | i | t | e |  | i | s |  | d | e | f | i | n | e | d |  | i | n |  | R | i | s | k | - | A | s | s | e | s | s | m | e | n | t | - | M | e | t | h | o | d | o | l | o | g | y | . | m | d | .