## Corrective Action Plan
Simulated portfolio project - HawkPay Technologies Pvt. Ltd. is fictional. Not a certification claim.
Finding | Root Cause | Corrective Action | Owner | Deadline (days) | Deadline | Status | Control | Verification
AF-001 | No scheduled restore testing | Quarterly backup restore test; keep signed test record | DevOps | 30 | 2026-11-07 | Open | A.8.13 | Re-test at next internal audit
AF-002 | Incomplete MFA rollout | Enforce MFA for all users; report coverage monthly | IT | 15 | 2026-10-23 | In Progress | A.5.17 | Re-test at next internal audit
AF-003 | No formal vendor process | Create vendor assessment questionnaire | Procurement | 60 | 2026-12-07 | Open | A.5.19 | Re-test at next internal audit
AF-004 | No access-review schedule | Quarterly privileged-access reviews with sign-off | CTO | 30 | 2026-11-07 | Open | A.5.15 | Re-test at next internal audit