## Audit Findings
Simulated portfolio project - SecurePay Technologies Pvt. Ltd. is fictional. Not a certification claim. AF-004 added to reflect the Partial access-review result.
Finding ID | Control | Finding | Severity | Risk | Corrective Action | Owner | Due (days) | Due Date | Status
AF-001 | A.8.13 | Backup restoration tests have not been performed within the defined review period. | Major | Recovery failure during a critical incident. | Conduct quarterly restoration testing and retain evidence. | DevOps Lead | 30 | 2026-11-07 | Open
AF-002 | A.5.17 | MFA is not enforced for all users (82% coverage). | Major | Account takeover of email, GitHub or VPN. | Enforce MFA for all users. | IT Manager | 15 | 2026-10-23 | Open
AF-003 | A.5.19 | No formal vendor security assessment process; assessments are partial. | Minor | Supply-chain compromise. | Create and apply a vendor assessment questionnaire. | Procurement | 60 | 2026-12-07 | Open
AF-004 | A.5.15 | Access reviews are ad hoc; only partly evidenced. | Minor | Excessive privileges persist undetected. | Run quarterly privileged-access reviews and retain reports. | CTO | 30 | 2026-11-07 | Open